INSTAWARD - STATEMENT OF WORK

30-Day Scoped Engagement

# 1. Project & Team Information

| Project Name | Shopble — Stablecoin Checkout & Order Reconciliation Prototype on Stellar (Phase 1) |
| --- | --- |
| Builder / Team Name | Shopble |
| Primary Contact | Luong Thi Hien ¦ hiennbami@gmail.com |
| Project’s Github | https://github.com/hiennbami-lab/Shopble---Stellar |
| Ambassador Chapter | Vietnam |
| Ambassador Chapter Lead | Tiffany Hoang |
| Date Submitted | August 6, 2026 |
| Suggested Sprint Start Date | August 10, 2026 (30-day sprint, ending September 8, 2026) |
| Wallet address | GAMEFAKCOIMPEZXD5PWQBLM565XNQ26ZD5GLNBFQ2ELRWNSGK7MMEX4M |

# 2. Instawards Overview & Intent

2.1 Instawards Purpose (for Builder Context)

Instawards are designed to support short, clearly scoped, execution-focused work that helps a project make tangible progress toward building on Stellar. Instawards are meant to fund specific, achievable outcomes that can be completed and demonstrated within 30 days or less.

This SOW represents a shared commitment between the Builder and the Ambassador Chapter Lead on what will be delivered, why it matters, and how success will be verified.

# 3. Problem Statement & Objective

| Problem Being Addressed | A buyer who already holds stablecoins on Stellar has no reliable way to have that payment recognised as settlement for one specific commerce order. Today the transfer and the order record live in two disconnected systems: a Stellar payment carries no order context beyond a free-text memo, and the order system has no deterministic way to prove that a given on-chain payment actually satisfies the expected amount, asset, destination account and buyer wallet for that order. Without that reconciliation layer, every downstream commerce feature — checkout, fulfilment eligibility, refunds, merchant settlement — is unbuildable, because none of them can trust that a payment belongs to the order it claims to pay for. This is the smallest piece of the system that has to be provably correct before anything else can be built on top of it. |
| --- | --- |
| Objective for this Instaward | At the end of this 30-day sprint, a reviewer can watch one complete, verifiable loop on Stellar TESTNET: 1. A buyer connects a Stellar wallet and creates an order intent. 2. The system generates a Stellar testnet payment instruction for that order. 3. The buyer sends the testnet stablecoin payment from their own wallet. 4. A backend watcher independently detects that payment on the ledger and captures its evidence (transaction hash, source, destination, asset, amount, memo, ledger close time). 5. A matching engine returns exactly one deterministic verdict: matched, or one of five typed rejections (underpayment, wrong asset, wrong destination, wrong buyer wallet, invalid memo/reference). 6. That verdict is written to a minimal Soroban contract on testnet, moving the order to validated (fulfilment-eligible) or to rejected with a stated reason. All work, all transactions and all evidence are on Stellar testnet. No real value moves. No real purchase, merchant settlement, shipment or custody of user funds occurs at any point in this scope. |

Example prompts for builders: What is currently preventing progress? What is unclear, missing, or unbuilt today? Why is this problem worth solving now?

# 4. Scope of Work (30-Day Deliverables)

Important guidance: This scope must be achievable within 30 calendar days. If the work feels larger, it should be reduced or split into more achievable phases.

4.1  In-Scope Deliverables

| Deliverable | Description (What will be built or produced?) | Why This Matters |
| --- | --- | --- |
| Deliverable 1 Wallet-Connected Order Intent & Testnet Payment Instruction | A web flow where a buyer connects a Stellar wallet (Freighter, via Stellar Wallets Kit) and creates an order intent. Each intent persists exactly seven fields: product/source context, expected amount, asset (a fixed testnet stablecoin, issuer stated in the repo README), destination account, memo/reference, connected buyer wallet address, and order/payment status. The system then generates the corresponding Stellar testnet payment instruction (destination, asset, amount, memo) and presents it both as a copyable payload and as a signable transaction. Verified by 10 documented runs across at least 3 distinct testnet wallets. Each run records all 7 stored fields and the generated instruction; any run that does not behave as expected is logged with its root cause rather than discarded. | Establishes the binding between a buyer wallet, a commerce order and one specific expected Stellar payment. Nothing downstream can be matched or validated until this binding exists and is stored consistently. |
| Deliverable 2 Testnet Payment Watcher & Deterministic Order Matching | A backend watcher that streams classic payment operations from Stellar Horizon (testnet) for the destination account, persists its cursor so ingestion is replay-safe, and captures evidence for every payment seen: transaction hash, source account, destination account, asset, amount, memo/reference and ledger close time. A matching engine then compares each captured payment against open order intents and returns exactly one verdict: matched, or one of five typed rejections — underpayment, wrong asset, wrong destination, wrong buyer wallet, invalid memo/reference. Duplicate payments against an already-settled order are detected and flagged separately. Verified by 15 documented testnet transactions covering matched cases and all five rejection types, each recorded with its transaction hash, a Stellar Expert (testnet) link, the expected verdict, the returned verdict, and detection latency from ledger close to capture. | Proves that a real on-chain payment can be read from the Stellar ledger and deterministically accepted or rejected against the correct commerce order. Every rejection carries an auditable, named reason — which is what makes the result trustworthy rather than merely plausible. |
| Deliverable 3 On-Chain Order Status Registry & Validation State Machine | A deliberately minimal Soroban contract deployed to Stellar testnet, storing order status on-chain via three functions: create_order(order_id, buyer, expected_amount, asset, memo_hash); set_status(order_id, status), guarded by operator authorisation; and get_order(order_id). Statuses follow one state machine: awaiting_payment → payment_detected → validated ¦ rejected(reason). Only validated marks an order fulfilment-eligible. The backend writes each matcher verdict from Deliverable 2 to the contract, so every transition is independently verifiable on-chain. Delivered as: the deployed testnet contract ID, the Rust source in the public repo, passing contract unit tests, and on-chain transaction links showing both a validated and a rejected order. Scope note: the contract stores status only. It holds no tokens, performs no transfers, implements no escrow and makes no cross-contract calls. | Moves the order-status decision out of a private database and into verifiable on-chain state. That is the prerequisite for any future non-custodial or multi-party settlement flow, where a merchant or a third party must be able to check an order's status without trusting Shopble's backend. |
| Out-of-Scope (Explicitly Not Included) List anything that might be assumed but is not included in this Instaward scope. |  |  |
| The following are explicitly NOT included in this Instaward: 1. Stellar mainnet. All work, transactions and evidence are testnet-only. No real value moves at any point. 2. Real purchasing, assisted checkout, merchant onboarding or approval, and any marketplace or storefront integration. 3. Fulfilment, shipping, refunds, chargebacks, dispute handling and customer support. 4. Custody of user funds, escrow, FX conversion, on-ramp/off-ramp routes and merchant settlement. 5. Production KYC/AML, production security hardening, third-party audit and load testing. 6. Asset issuance beyond the single fixed testnet stablecoin used for testing. 7. Mobile applications and production-grade UI/UX. The interface delivered is a functional demo sufficient to verify the flow, nothing more. |  |  |

4.2  Deliverable-Aligned Budget Request

| Category | Amount | % | Description |
| --- | --- | --- | --- |
| Wallet-Linked Order Intent & Payment Instruction | $900 | 18% | Wallet connection via Stellar Wallets Kit / Freighter, order-intent API and data model, 7-field persistence, and testnet payment-instruction generation. |
| Testnet Payment Watcher | $900 | 18% | Horizon testnet payment streaming, cursor persistence and replay-safe ingestion, evidence capture (tx hash, source, destination, asset, amount, memo, ledger close time). |
| Payment Matching & Reject-Case Engine | $900 | 18% | Deterministic matching rule, five typed rejection reasons, duplicate-payment detection, and per-payment verdict logging. |
| Validation State Machine | $600 | 12% | Order and payment status model, transition guards, fulfilment-eligibility gate, and a reviewer-readable status view. |
| Minimal Soroban Order-Status Contract | $1,100 | 22% | Rust / soroban-sdk contract (create_order, set_status, get_order), unit tests, testnet deployment, and backend integration via Stellar RPC. |
| Test Campaign, Evidence Pack & Demo | $600 | 12% | 25 documented testnet runs, results tables, transaction-hash index with explorer links, screen recording, README and submission packet. |
| TOTAL | $5,000 | 100% | Instawards cap: $5,000. This request is at the cap and every line item above maps to specific days in the Section 5 timeline. |

# 5. 30-Day Execution Plan & Timeline

5.1 Weekly Breakdown

| Week | Planned Work | Expected Output |
| --- | --- | --- |
| Week 1 | Day 1–2 — Soroban risk spike (go/no-go gate). Install Stellar CLI 26.x and the Rust wasm32 toolchain, build and deploy the hello-world contract to testnet, invoke it from the CLI and from JS via Stellar RPC. This front-loads the single biggest technical unknown so it is resolved on Day 2 rather than Day 20. Day 3–4 — Order and payment data model. Define the seven order-intent fields, fix the testnet stablecoin asset and issuer, set the destination account, design the memo reference scheme (28-byte limit) and write the full status map. Day 5–7 — Wallet connection (Freighter via Stellar Wallets Kit) and the order-intent creation API with persistence. | A deployed hello-world contract ID on testnet, confirming the Soroban toolchain works end to end. A documented data model, asset/issuer decision and status map committed to the repo. A buyer can connect a Stellar wallet and create a stored order intent containing all seven fields. |
| Week 2 | Day 8–9 — Payment-instruction generator: destination, asset, amount and memo, rendered both as a copyable payload and as a signable transaction. Day 10–12 — Horizon testnet payment watcher: SSE streaming of payment operations for the destination account, cursor persistence in the database, replay-safe ingestion, and evidence capture for every payment observed. Day 13–14 — First end-to-end pass: create an intent, pay it from a second testnet wallet, confirm the watcher captures the payment with its transaction hash. | Every order intent produces a valid, payable Stellar testnet payment instruction. A running watcher that stores captured payment evidence and survives restart without losing or double-counting payments. At least 3 captured testnet payments linked to their pending order intents. |
| Week 3 | Day 15–17 — Matching engine: deterministic comparison of captured payment against open intents, the five typed rejection reasons, and duplicate-payment detection. Day 18–19 — Validation state machine and fulfilment-eligibility gate, plus a reviewer-readable status view showing expected-versus-observed fields per order. Day 20–21 — Soroban order-status contract: write, unit-test, deploy to testnet, and wire the backend so each matcher verdict is written on-chain. | Every captured payment returns exactly one verdict, with a named reason for each rejection. A deployed testnet contract ID, with on-chain status transitions visible for both a matched order and a rejected order. |
| Week 4 | Day 22–25 — Test campaign: 10 order-intent runs across at least 3 distinct testnet wallets, and 15 watcher transactions covering matched cases plus all five rejection types. Every result is logged as it happens, including any run that deviates from the expected verdict. Day 26–27 — Evidence pack: results tables, transaction-hash index with Stellar Expert (testnet) links, contract ID and on-chain transaction links. Day 28–29 — Screen recording of the full loop plus two rejection cases; README and setup instructions in the public repo. Day 30 — Buffer, final review, and submission of the evidence packet to the Ambassador Chapter Lead. | A complete evidence pack: 25 documented runs with transaction hashes and explorer links. A public GitHub repository with README, setup instructions and contract source. A 5–8 minute screen recording of the end-to-end flow, and the submitted deliverables packet. |

# 6. Evidence of Completion (Required)

Important guidance: Evidence should be clear, verifiable, and easy to review by the Ambassador Chapter Lead with minimal technical expertise.

6.1  Planned Evidence to Be Submitted

| Deliverable | Evidence Type (link, repo, demo, screenshot, doc, tx hash, etc.) | Description |
| --- | --- | --- |
| Deliverable 1 Wallet-Connected Order Intent & Testnet Payment Instruction | Public GitHub repository link Results table (10 runs) Screen recording | Repo link to the order-intent service and wallet connection code. A results table of 10 documented runs across at least 3 distinct testnet wallets, each row showing all seven stored fields and the generated payment instruction. A short recording of two full runs from wallet connection to instruction generation. |
| Deliverable 2 Testnet Payment Watcher & Deterministic Order Matching | Transaction-hash index Stellar Expert (testnet) links Results table (15 tx) | A table of 15 testnet transactions. Each row carries the transaction hash, a clickable Stellar Expert testnet link, the expected verdict, the verdict actually returned, and the detection latency from ledger close to capture. Coverage includes matched cases and all five rejection types: underpayment, wrong asset, wrong destination, wrong buyer wallet, invalid memo/reference. |
| Deliverable 3 On-Chain Order Status Registry & Validation State Machine | Deployed contract ID On-chain transaction links Contract source + unit tests | The Soroban testnet contract ID, plus links to the on-chain transactions showing the transitions awaiting_payment → payment_detected → validated, and a second order going to rejected with its reason. Rust source in the public repo with passing unit tests. |
| Overall End-to-end demonstration | Screen recording (5–8 minutes) | One unbroken walkthrough: connect wallet, create order intent, pay on testnet, watcher detects the payment, matcher validates it, on-chain status updates to validated. Followed by two rejection cases showing the named reason. Recorded so it can be followed without technical expertise. |

6.2  Evidence Verification Checklist (Ambassador Use)

For each deliverable, the Ambassador Chapter Lead will assess whether evidence is present and sufficient.

| Deliverable | Present | Partial | Missing | Comments |
| --- | --- | --- | --- | --- |
| Deliverable 1 — Wallet-Connected Order Intent & Testnet Payment Instruction | ☐ | ☐ | ☐ |  |
| Deliverable 2 — Testnet Payment Watcher & Deterministic Order Matching | ☐ | ☐ | ☐ |  |
| Deliverable 3 — On-Chain Order Status Registry & Validation State Machine | ☐ | ☐ | ☐ |  |
| Overall — End-to-end demonstration recording | ☐ | ☐ | ☐ |  |

# 7. Next-Step Alignment

7.1. Anticipated Next Step After Completion

After this Instaward, the most likely next step is:

☑  Apply to SCF Build Award

☐  Continue development independently

☑  Apply for a follow-on Instaward (if eligible)

☐  Seek other ecosystem support (Stellar × CV Labs Accelerator, B2B wallet integration)

☐  Other

# 8. Instawards Constraints Acknowledgement

By submitting this SOW, the Builder acknowledges:

☑  This scope will be completed within 30 days or less.

☑  Instawards support execution, not open-ended exploration.

☑  A project may receive no more than two follow-on Instawards.

☑  Each Instaward is capped at $5,000.

☑  Total Instawards funding may not exceed $15,000.

# 9. Submission Confirmation

Once finalized, this Statement of Work will be submitted by the Ambassador Chapter Lead via the Instawards Airtable submission form for review and approval.